FINANCIAL ANALYSIS — DOCUMENT 04.1  |  DATA ROOM

Indicative Financial Analysis

Nairn Ni Cu PGE Project — Exploration Economics & Scenario Modelling

IMPORTANT DISCLAIMER

This document presents indicative, conceptual financial analysis only. It is NOT an NI 43-101 mineral resource estimate, a preliminary economic assessment (PEA), a pre-feasibility study, or a feasibility study. No resource has been defined at Nairn. All scenarios are hypothetical and are provided solely to illustrate the potential economic scale of a discovery relative to exploration cost. This analysis should not be relied upon for investment decisions. Independent due diligence by a qualified person is required.

# Exploration Budget — Phase 1 to Resource

The following budget outlines the estimated cost to advance the Nairn property from its current early-exploration stage to a maiden NI 43-101 mineral resource estimate. All figures are in Canadian dollars and represent a reasonable range based on current Sudbury-area drilling and geophysics contractor rates.

| Phase | Scope | Timeline | Budget (CAD) |
| --- | --- | --- | --- |
| Phase 1A | IP geophysics (2,500 line-m) + ground EM (VTEM follow-up, 600 m) | 3–4 months | $180,000–$250,000 |
| Phase 1B | 5–8 diamond drill holes (avg 400m depth; ~2,800 m total) | 4–6 months | $1,050,000–$1,680,000 |
| Phase 1 QA/QC | Modern assay program, QA/QC, geological logging, compilation | Concurrent | $120,000–$200,000 |
| Phase 1 G&A | Management, camp, transport, insurance, consultation | Concurrent | $150,000–$250,000 |
| Phase 1 Total | First-pass geophysics + drilling program | ~9–12 months | $1,500,000–$2,380,000 |
| Phase 2A | Step-out drilling: 8–15 holes (~5,000 m) to define maiden resource | 6–9 months | $1,875,000–$3,750,000 |
| Phase 2B | Resource modelling, NI 43-101 compliant resource estimate | 4–6 months | $300,000–$500,000 |
| Phase 2 Total | Resource definition program | ~12 months | $2,175,000–$4,250,000 |
| Phase 3 | PEA / scoping study (if Phase 2 defines +3 Mt @ +1.0% Ni Eq) | 6–9 months | $800,000–$1,500,000 |

Budget ranges based on 2024-25 Ontario contractor rates. Drilling at CAD 375–600/m (underground access not required for Phase 1). Camp costs CAD 450–600/person-day. IP geophysics CAD 60–90/station.

# Metal Price Assumptions

Three price scenarios are used throughout this analysis — Bear, Base, and Bull — reflecting a range of nickel market conditions. Nickel has historically exhibited significant volatility (ranging from USD 8,000 to USD 48,000/t over the past decade). The Base Case reflects consensus analyst forward curves as of mid-2025, incorporating energy-transition demand growth offset by Indonesian supply increases.

| Metal | Bear Case | Base Case | Bull Case | Unit |
| --- | --- | --- | --- | --- |
| Nickel (LME) | USD 12,000 | USD 17,000 | USD 24,000 | per tonne |
| Copper (LME) | USD 8,000 | USD 10,500 | USD 13,000 | per tonne |
| Cobalt (LME) | USD 25,000 | USD 40,000 | USD 55,000 | per tonne |
| Platinum (LBMA) | USD 850 | USD 1,050 | USD 1,400 | per troy oz |
| Palladium (LBMA) | USD 900 | USD 1,100 | USD 1,600 | per troy oz |
| CAD/USD FX | 0.70 | 0.73 | 0.76 | ratio |

# NiEq Grade Calculation

For scenario modelling purposes, a Nickel Equivalent (NiEq) grade is calculated to reduce the polymetallic deposit to a single comparable metric. At Base Case metals prices:

- NiEq (%) = Ni% + (Cu% × 0.62) + (Co% × 2.35) + (Pt g/t × 0.062) + (Pd g/t × 0.065)

This formula applies standard payability factors (85% Ni, 87% Cu, 72% Co) and smelter penalties typical for a Sudbury sulphide concentrate. The resulting NiEq grades align with industry-standard reporting practices used by Vale, Glencore, and KGHM for comparable Sudbury deposits.

# Hypothetical Resource Scenarios

The following scenarios illustrate what a range of discovery outcomes would mean in terms of NiEq metal content and in-situ gross metal value. These are HYPOTHETICAL — no resource has been estimated at Nairn. The Totten and Victoria analogues are based on actual published resources at those projects, provided to show what is geologically possible on the same dyke system.

| Scenario | Tonnes (Mt) | Ni Grade (%) | Cu Grade (%) | NiEq Grade (%) | NiEq Metal (t) | In-Situ Value @USD17k/t Ni |
| --- | --- | --- | --- | --- | --- | --- |
| Small | 2.0 | 1.0% | 0.5% | ~1.25% | 25,000 t | ~CAD 580M |
| Base | 5.0 | 1.2% | 0.7% | ~1.57% | 78,500 t | ~CAD 1.8B |
| Optimistic | 10.0 | 1.5% | 1.0% | ~1.98% | 198,000 t | ~CAD 4.6B |
| Totten Analogue | 10.5 | 1.5% | 2.0% | ~2.37% | 249,000 t | ~CAD 5.8B |
| Victoria Analogue | 14.5 | 2.5% | 2.5% | ~3.25% | 471,000 t | ~CAD 11.0B |

NiEq calculated at Base Case metal prices. In-situ value assumes 100% NiEq at USD 17,000/t Ni price (CAD 23,290/t at 0.73 FX). In-situ value is gross undiscounted metal value with no processing or capital cost deductions — it is an order-of-magnitude indicator only, not a recoverable or economic value.

# Acquirer Return Analysis

The table below illustrates the potential return to an acquiring party that funds a Phase 1 + Phase 2 exploration program through to a maiden resource estimate, under the three discovery scenarios. Market capitalisation re-ratings are based on $/t NiEq valuations observed in junior mining M&A transactions in the Sudbury Basin and comparable Canadian nickel districts.

| Metric | Bear | Base | Bull | Notes |
| --- | --- | --- | --- | --- |
| Exploration cost (Phase 1+2) | CAD 3M | CAD 4M | CAD 6M | Direct program cost |
| Discovery resource (NiEq) | 25,000 t | 78,500 t | 249,000 t | NiEq metal |
| Implied discovery cost ($/t NiEq) | CAD 120 | CAD 51 | CAD 24 | Industry avg ~USD 50–150 |
| Market cap re-rating (USD/t NiEq) | USD 200 | USD 400 | USD 650 | Junior Sudbury precedent |
| Implied market cap post-discovery | CAD 7M | CAD 43M | CAD 215M | Pre-PEA valuation |
| Uplift from Phase 1 cost of CAD 2M | 3.5× | 21.5× | 107× | Return on exploration $ |

Market cap valuations are illustrative only, based on historical $/t NiEq transaction and market multiples for pre-PEA Sudbury juniors. Actual returns depend on resource grade, size, metallurgy, capital markets conditions, and deal structure.

# Sudbury Operating Cost Benchmarks

For reference in understanding the economics of a potential future Nairn operation, the following benchmarks reflect typical Sudbury underground Ni-Cu mine parameters, based on public disclosures by Vale and Glencore:

| Mining Method | Long-hole open stoping or cut-and-fill; typical for tabular/lens SOD bodies |
| --- | --- |
| Underground Mining Cost | CAD 75–110 / tonne mined (Sudbury operators, 2022–24 avg) |
| Processing Cost (milling) | CAD 20–35 / tonne milled (processing to sulphide concentrate) |
| G&A Cost | CAD 10–20 / tonne mined |
| Smelting / Refining | Sudbury smelters within 25–50 km; TC/RC typically 10–12% of Ni value |
| Total AISC (Sudbury range) | USD 3.50–6.00 / lb Ni (USD 7,700–13,200 / t Ni) — world competitive |
| Typical Ore Recovery | 85–92% sulphide flotation recovery for Sudbury massive sulphide |
| Water Management | Dewatering required for underground; Sudbury precedent for tailings management |

At base-case nickel prices of USD 17,000/t and AISC of USD 9,000/t, operating cash margins of approximately USD 8,000/t Ni are achievable for a Sudbury deposit — consistent with the high profitability of active Sudbury mines.

# Government Grants & Tax Incentives

A Phase 1 program at Nairn may be eligible for several Ontario and federal programs that materially reduce the net cost to an acquiring company:

| Program | Details | Typical Value |
| --- | --- | --- |
| Ontario Junior Exploration Program (OJEP) | Grant for pre-commercial exploration on Ontario mining claims; eligible for drilling and geophysics | Up to CAD 200,000 / year |
| Ontario Flow-Through Shares (FTS) | Canadian tax incentive allowing 100% deduction + 15% FTS credit on eligible exploration expenditures | Reduces effective exploration cost ~45% |
| Critical Mineral Infrastructure Fund (CMIF) | Federal program for road, power, and infrastructure supporting critical mineral projects | CAD 50M–500M |
| Ontario Focused Flow-Through (OFFT) | Ontario refundable tax credit for qualifying exploration expenditures in Ontario | 5% refundable credit on METC-eligible spend |
| NOHFC — Northern Ontario Fund | Supports economic development in Northern Ontario including mining exploration | Up to CAD 1M (grants/loans) |

Under flow-through share financing at a 45% effective tax credit rate, a CAD 2 million Phase 1 program effectively costs the company approximately CAD 1.1 million in net exploration expenditure — significantly improving the risk-adjusted return on the exploration investment.

DISCLAIMER

This analysis is prepared for indicative purposes only and does not constitute an NI 43-101 technical report, PEA, pre-feasibility study, or investment advice. No mineral resource or reserve has been estimated at Nairn. All resource scenarios, financial projections, and return calculations are hypothetical and forward-looking statements subject to material risks. Metal prices, exchange rates, operating costs, and recoveries are assumptions only. Past exploration results at adjacent properties are not necessarily indicative of the results that may be obtained at Nairn. Prospective parties must conduct independent due diligence with qualified technical and financial advisors.